PLANIFICATION D'EXÉCUTION : Scénario 2 - Adaptation Auto-Claude vers Auto-Gemini-CLI

Version: 1.0
Date: 2 janvier 2026
Équipe: Desjardins | Architect: André-Guy Bruneau
Budget: $13-34K | Timeline: 14 semaines (3.5 mois)
Début prévu: 6 janvier 2026 | Livraison v1.0: 1er mai 2026

TABLE DES MATIÈRES

- Structure Exécution

- Phase 0: Préparation (Semaines 1-2)

- Phase 1: Swap API (Semaines 3-5)

- Phase 2: Migration UI (Semaines 6-8)

- Phase 3: Optimisation Gemini (Semaines 9-12)

- Phase 4: Intégration & Release (Semaines 13-14)

- Dépendances & Blockers

- Métriques de Succès

- Gestion des Risques

- Budget Détaillé

STRUCTURE EXÉCUTION

Allocation Ressources

Équipe: 1.5 FTE (14 semaines)
├── Lead Architect (1.0 FTE)
│ ├── Design & decision-making
│ ├── Code review & integration
│ └── Stakeholder communication
│
└── Senior Developer (0.5 FTE)
├── Feature implementation
├── Testing & debugging
└── Documentation support

Timeline Critique

Phase 0: Préparation Semaines 1-2 (Jan 6-19, 2026)
Phase 1: Swap API Semaines 3-5 (Jan 20 - Feb 9, 2026)
Phase 2: Migration UI Semaines 6-8 (Feb 10 - Mar 2, 2026)
Phase 3: Optimisation Semaines 9-12 (Mar 3 - Mar 30, 2026)
Phase 4: Release Semaines 13-14 (Mar 31 - Apr 13, 2026)

Réserve: 2-3 semaines (buffer pour imprévu)
─────────────────────────────────────────────
Total: 14 semaines → v1.0 livraison ~1er mai 2026

Gouvernance

| Rôle | Responsable | Fréquence |
| --- | --- | --- |
| Project Lead | André-Guy Bruneau | Quotidien |
| Sprint Reviews | Team + Stakeholders | Bi-hebdomadaire |
| Gate Decisions | Leadership + Arch | Fin de chaque phase |
| Risk Management | Project Lead | Hebdomadaire |

PHASE 0: PRÉPARATION (Semaines 1-2)

Objectif: Sécuriser ressources, configurer infrastructure, analyser codebase
Deliverables: Repository setup, team onboarding, architectural ADRs
Success Criteria: MVP plan révisé, team 100% ready, no technical unknowns

Semaine 1 (6-12 janvier 2026)

Jour 1-2: Approval & Setup

- [ ] Tâche 1.1: Obtenir approbation budgétaire formelle Desjardins

  - Owner: André-Guy (Lead Arch)

  - Deliverable: Signed approval document

  - Effort: 4h (réunions + documentation)

  - Dépendance: Sponsor exécutif disponible

- [ ] Tâche 1.2: Créer repository GitHub (fork Auto-Claude)

  - Owner: André-Guy (Lead Arch)

  - Deliverable: agbruneau/auto-gemini-cli repository

  - Effort: 2h (fork + cleanup)

  - Steps:

Create private fork

gh repo fork auto-claude-repo --clone --private

Remove unnecessary files (Electron dependencies)

rm -rf electron/ dist/ build/
git commit -m "chore: remove electron dependencies"

Initialize fresh Git history

git log | head -20 # Verify history preserved

- [ ] Tâche 1.3: Créer projet management & backlog

  - Owner: André-Guy (Lead Arch)

  - Deliverable: GitHub Project avec tous les epics

  - Effort: 3h (structure + tagging)

  - Structure:
GitHub Project: Auto-Gemini-CLI Execution
├── Phase 0: Préparation
├── Phase 1: API Swap
├── Phase 2: UI Migration
├── Phase 3: Optimisation
└── Phase 4: Release

Labels:

    - critical (blocks other work)

    - high (important, may block)

    - medium (nice to have)

    - testing (QA/test related)

    - documentation (docs/examples)

    - infrastructure (CI/CD, tools)

Jour 2-3: Codebase Analysis

- [ ] Tâche 1.4: Audit architectural Auto-Claude

  - Owner: Senior Dev + Lead Arch

  - Deliverable: Architecture analysis document

  - Effort: 8h (code review + documentation)

  - Scope:

Auto-Claude Architecture Audit

Current Structure

    - Total LOC: ~[count]

    - Main modules:

      - Agent engine: [module_name]

      - Claude SDK integration: [module_name]

      - Session management: [module_name]

      - Git workflows: [module_name]

      - UI/Electron layer: [module_name]

Electron Dependencies

    - Direct: [list]

    - Transitive: [list]

    - Removal risk: [assessment]

Claude-Specific Code

    - Token counting: [lines affected]

    - Streaming: [lines affected]

    - Error handling: [lines affected]

    - Model parameters: [lines affected]

Reusable Modules

    - [module]: 100% reusable

    - [module]: 90% reusable (minor tweaks)

    - [module]: 50% reusable (needs refactor)

Technical Debt

    - [issue]: Severity [HIGH/MEDIUM/LOW]

    - [issue]: Severity [HIGH/MEDIUM/LOW]

- [ ] Tâche 1.5: Identifier Gemini API incompatibilities

  - Owner: Senior Dev

  - Deliverable: Migration checklist

  - Effort: 6h

  - Checklist:

Claude → Gemini API Mapping

Token Counting

    - [ ] Claude: countTokens(prompt)

    - [ ] Gemini: countTokens() method signature

    - [ ] Difference in handling: [document]

Streaming

    - [ ] Claude: stream() event interface

    - [ ] Gemini: streaming in @google/genai v0.4

    - [ ] Adapter pattern needed: YES/NO

Error Handling

    - [ ] Claude error codes: [list]

    - [ ] Gemini error codes: [list]

    - [ ] Mapping required: [details]

Rate Limiting

    - [ ] Claude: per-model limits

    - [ ] Gemini: 1000 req/24h free tier

    - [ ] Queue system: Design required

Model Parameters

    - [ ] temperature, topK, topP, etc.

    - [ ] Direct compatibility: YES/NO

    - [ ] Parameter translation needed: [list]

Function Calling

    - [ ] Claude: tool_use blocks

    - [ ] Gemini: function_calling (different syntax)

    - [ ] Refactor required: [scope]

Jour 4-5: Team & Tooling

- [ ] Tâche 1.6: Team onboarding & Git setup

  - Owner: Lead Arch

  - Deliverable: Team setup complete

  - Effort: 4h

  - Checklist:

Team Onboarding

    - [ ] Access to repository granted

    - [ ] Desjardins VPN/network configured

    - [ ] GitHub CLI setup (gh auth login)

    - [ ] Local environment config:

      - Node 20+ installed

      - TypeScript 5+ installed

      - Oclif CLI installed globally

      - Gemini API key set (GEMINI_API_KEY env var)

    - [ ] IDE setup: VS Code/Cursor with extensions

      - TypeScript language server

      - ESLint + Prettier

      - GitHub Copilot (optional)

    - [ ] SSH keys configured for git

- [ ] Tâche 1.7: Setup CI/CD pipeline

  - Owner: Lead Arch

  - Deliverable: GitHub Actions workflows

  - Effort: 4h

  - Workflows to create:

.github/workflows/test.yml

name: Unit & Integration Tests
on: [push, pull_request]
jobs:
test:
runs-on: ubuntu-latest
steps:
- uses: actions/checkout@v4
- uses: actions/setup-node@v4
with:
node-version: '20'
- run: npm ci
- run: npm run test
- run: npm run lint

.github/workflows/e2e.yml

name: E2E Tests (Gemini)
on: [push]
jobs:
e2e:
runs-on: ubuntu-latest
steps:
- uses: actions/checkout@v4
- uses: actions/setup-node@v4
- run: npm ci
- run: npm run test:e2e
env:
GEMINI_API_KEY: ${{ secrets.GEMINI_API_KEY }}

Semaine 2 (13-19 janvier 2026)

Jour 6-7: Architecture & Design

- [ ] Tâche 2.1: Write Architecture Decision Records (ADRs)

  - Owner: Lead Arch

  - Deliverable: 3-5 ADRs in /docs/adr/

  - Effort: 6h

  - ADRs to document:

ADR-001: Why Oclif instead of Yargs/Commander

    - Context: Need native CLI framework for Gemini

    - Decision: Use Oclif (Salesforce-backed, TypeScript-first)

    - Rationale: Auto-Claude uses similar patterns

    - Consequences: Learning curve minimal, ecosystem strong

ADR-002: Session Persistence Strategy

    - Context: Need to persist sessions (SQLite vs JSON)

    - Decision: Keep SQLite (from Auto-Claude)

    - Rationale: Proven, ACID, supports multi-session

    - Consequences: SQLite dependency required

ADR-003: Rate Limiting Architecture

    - Context: 1000 req/24h Gemini limit

    - Decision: Token-bucket queue + persistent state

    - Rationale: Fair distribution, survives restarts

    - Consequences: Redis or SQLite-backed queue needed

ADR-004: Token Counter Validation

    - Context: countTokens() API differs Claude vs Gemini

    - Decision: Wrapper + unit tests with known inputs

    - Rationale: Prevents context window overflows

    - Consequences: Must validate against real Gemini API

ADR-005: Error Recovery Patterns

    - Context: Gemini SDK may have breaking changes

    - Decision: Adapter pattern for API layer

    - Rationale: Decouples business logic from SDK

    - Consequences: Extra abstraction layer (+10% complexity)

- [ ] Tâche 2.2: Create detailed Phase 1 spec

  - Owner: Lead Arch

  - Deliverable: /docs/phase-1-spec.md

  - Effort: 5h

  - Content:

Phase 1 Detailed Specification

Objective

Replace Claude SDK with Gemini SDK, verify basic functionality works

In-Scope

    - Gemini SDK integration (@google/genai v0.4)

    - Basic model.generateContent() parity

    - Token counter validation

    - Error mapping (Claude codes → Gemini codes)

Out-of-Scope

    - UI/CLI layer (Phase 2)

    - Performance optimization (Phase 3)

    - Multi-model support

Acceptance Criteria

    - [ ] Single task executes end-to-end with Gemini

    - [ ] countTokens() validates context windows

    - [ ] At least 80% of existing tests pass

    - [ ] No blocking errors in E2E flow

    - [ ] Documented API differences

Technical Details

SDK Migration

  - Before (Claude):
import { Anthropic } from "@anthropic-ai/sdk";
const client = new Anthropic({ apiKey: process.env.CLAUDE_API_KEY });
const response = await client.messages.create({ ... });

  - After (Gemini):
import { GoogleGenAI } from "@google/genai";
const client = new GoogleGenAI({ apiKey: process.env.GEMINI_API_KEY });
const response = await client.models.generateContent({ ... });

File Structure Changes

    - Create: src/adapters/gemini-api-adapter.ts

    - Refactor: src/services/llm-service.ts (abstraction layer)

    - Delete: src/integrations/claude-specific/*

    - Update: All tests to use adapter

Testing Strategy

    - Unit tests: Adapter layer (mocked Gemini API)

    - Integration: Mocked responses (don't hit real API yet)

    - E2E: Real Gemini API (phase 1 gate decision)

Jour 8-10: Knowledge Transfer & Planning

- [ ] Tâche 2.3: Knowledge transfer from Auto-Claude author

  - Owner: Senior Dev (receiver)

  - Deliverable: Meeting notes + recorded session

  - Effort: 4h

  - Topics to cover:

    - Architecture decisions made in Auto-Claude

    - Known pain points & technical debt

    - Why certain patterns were chosen

    - Future roadmap intentions

    - Gotchas/tricks not documented

- [ ] Tâche 2.4: Finalize detailed task breakdown

  - Owner: Lead Arch

  - Deliverable: Updated GitHub Project backlog

  - Effort: 4h

  - Output: Every task has:

    - Clear acceptance criteria

    - Effort estimate (days, not story points)

    - Assigned owner

    - Blocking dependencies identified

    - Test strategy defined

- [ ] Tâche 2.5: Setup monitoring & observability

  - Owner: Lead Arch

  - Deliverable: Logging + error tracking configured

  - Effort: 3h

  - Tools:

Observability Stack

Logging

    - Framework: Winston or Pino

    - Levels: debug, info, warn, error

    - Output: stdout + file (for debugging)

Error Tracking

    - Tool: Sentry (free tier) or GCP Error Reporting

    - Integration: Auto-catch unhandled errors

    - Notifications: Slack #auto-gemini-errors channel

Performance Monitoring

    - Framework: Native Node.js perf hooks

    - Key metrics:

      - API response time (Gemini)

      - Token counting duration

      - Session load time

      - Memory usage

Health Checks

    - Endpoint: --health-check command

    - Metrics: Can call Gemini API, can access DB, can read config

Semaine 2 Closure

- [ ] Tâche 2.6: Pre-Phase-1 checkpoint

  - Owner: Lead Arch

  - Deliverable: Go/No-Go decision

  - Effort: 2h

  - Checkpoint questions:

Pre-Phase-1 Gate

    - [ ] Do we understand Auto-Claude architecture fully?

    - [ ] Have we identified all Gemini API incompatibilities?

    - [ ] Is the team 100% ready technically?

    - [ ] Do we have clear acceptance criteria for Phase 1?

    - [ ] Are there any unknown blockers?

    - [ ] Budget and timeline still realistic?

  - Decision: ☐ GO (proceed to Phase 1) ☐ NO-GO (re-plan)

If NO-GO:

    - Identified blocker: [description]

    - Time impact: [days/weeks]

    - Mitigation: [strategy]

PHASE 1: SWAP API (Semaines 3-5)

Objectif: Remplacer Claude SDK par Gemini SDK, validée fonctionnalité basique
Livrable: API layer complète, tests > 80% passing, MVP end-to-end
Succès: Single task fonctionne avec Gemini, no compilation errors

Semaine 3 (20-26 janvier 2026)

Jour 11: Foundation & Gemini SDK Integration

- [ ] Tâche 3.1: Créer adapter pattern pour LLM

  - Owner: Senior Dev

  - Deliverable: src/adapters/gemini-api-adapter.ts

  - Effort: 6h

  - Code structure:
// src/adapters/types.ts
export interface LLMAdapter {
generateContent(request: GenerateRequest): Promise<GenerateResponse>;
countTokens(request: CountTokensRequest): Promise<CountTokensResponse>;
startChat(config: ChatConfig): Promise<ChatSession>;
}

export interface GenerateRequest {
prompt: string;
systemPrompt?: string;
model: string;
temperature?: number;
maxOutputTokens?: number;
}

export interface GenerateResponse {
content: string;
inputTokens: number;
outputTokens: number;
finishReason: 'stop' | 'max_tokens' | 'safety' | 'unknown';
}

// src/adapters/gemini-api-adapter.ts
import { GoogleGenAI } from "@google/genai";

export class GeminiAPIAdapter implements LLMAdapter {
private client: GoogleGenAI;

constructor(apiKey: string) {
this.client = new GoogleGenAI({ apiKey });
}

async generateContent(request: GenerateRequest): Promise<GenerateResponse> {
const response = await this.client.models.generateContent({
model: request.model || "gemini-2.0-flash",
contents: request.prompt,
config: {
temperature: request.temperature,
maxOutputTokens: request.maxOutputTokens,
},
});

return {
  content: response.text || "",
  inputTokens: response.usage?.inputTokens || 0,
  outputTokens: response.usage?.outputTokens || 0,
  finishReason: this.mapFinishReason(response.candidates?.[0]?.finishReason),
};

}

async countTokens(request: CountTokensRequest): Promise<CountTokensResponse> {
const response = await this.client.models.countTokens({
model: request.model || "gemini-2.0-flash",
contents: request.prompt,
});

return {
  totalTokens: response.totalTokens,
};

}

private mapFinishReason(geminiReason?: string): string {
const mapping: Record<string, string> = {
'FINISH_REASON_STOP': 'stop',
'FINISH_REASON_MAX_TOKENS': 'max_tokens',
'FINISH_REASON_SAFETY': 'safety',
};
return mapping[geminiReason || ''] || 'unknown';
}
}

// src/services/llm-service.ts (refactored)
export class LLMService {
constructor(private adapter: LLMAdapter) {}

async chat(prompt: string, context?: ConversationContext): Promise<string> {
const response = await this.adapter.generateContent({
prompt,
systemPrompt: context?.systemPrompt,
model: context?.model || "gemini-2.0-flash",
});

return response.content;

}

async validateContext(prompt: string): Promise<boolean> {
const tokens = await this.adapter.countTokens({
prompt,
model: "gemini-2.0-flash",
});
return tokens.totalTokens < 1_000_000; // 1M token window
}
}

- [ ] Tâche 3.2: Update package.json dependencies

  - Owner: Senior Dev

  - Deliverable: Updated package.json

  - Effort: 1h

  - Changes:
{
"dependencies": {
"remove": ["@anthropic-ai/sdk"],
"add": ["@google/genai@^0.4.0"],
"keep": ["oclif (or similar)", "sqlite3", "commander or yargs"]
},
"devDependencies": {
"keep": ["typescript@5+", "vitest", "eslint", "prettier"]
}
}

npm uninstall @anthropic-ai/sdk
npm install @google/genai@^0.4.0
npm install # Reinstall lock file

- [ ] Tâche 3.3: Environment config & secrets

  - Owner: Lead Arch

  - Deliverable: .env.example + config module

  - Effort: 2h

  - File: src/config/environment.ts:
import dotenv from 'dotenv';

dotenv.config();

export const config = {
gemini: {
apiKey: process.env.GEMINI_API_KEY || '',
model: process.env.GEMINI_MODEL || 'gemini-2.0-flash',
maxTokens: parseInt(process.env.GEMINI_MAX_TOKENS || '1000000'),
},
app: {
logLevel: process.env.LOG_LEVEL || 'info',
dataDir: process.env.DATA_DIR || './data',
},
};

// Validation
if (!config.gemini.apiKey) {
throw new Error('GEMINI_API_KEY not set');
}

Jour 12-13: Basic Implementation

- [ ] Tâche 3.4: Implement GeminiAPIAdapter fully

  - Owner: Senior Dev

  - Deliverable: Complete adapter with streaming support

  - Effort: 8h

  - Features:

    - [x] generateContent() (unstreamed)

    - [x] generateContent() (streamed)

    - [x] countTokens()

    - [x] Error handling & mapping

    - [x] Rate limit handling (basic)

- [ ] Tâche 3.5: Create unit tests for adapter

  - Owner: Senior Dev

  - Deliverable: tests/adapters/gemini-api-adapter.test.ts

  - Effort: 6h

  - Test coverage:
describe('GeminiAPIAdapter', () => {
describe('generateContent', () => {
it('should return valid response for simple prompt', async () => {
// Mock Gemini API response
const response = await adapter.generateContent({
prompt: 'Hello world',
});
expect(response.content).toBeDefined();
expect(response.inputTokens).toBeGreaterThan(0);
});

it('should handle streaming responses', async () => {
  // Verify stream chunks accumulate
});

it('should map Gemini errors correctly', async () => {
  // Test error mapping
});

});

describe('countTokens', () => {
it('should accurately count tokens for known inputs', async () => {
const response = await adapter.countTokens({
prompt: 'Hello',
});
expect(response.totalTokens).toBe(2); // ~2 tokens for "Hello"
});
});
});

Semaine 4 (27 janvier - 2 février 2026)

Jour 14-15: Refactor Core Logic

- [ ] Tâche 4.1: Refactor Agent Engine for Gemini

  - Owner: Senior Dev + Lead Arch

  - Deliverable: Updated agent logic, tests passing

  - Effort: 10h

  - Scope:

    - Replace all client.messages.create() calls with adapter

    - Adapt function calling syntax (Claude tool_use → Gemini function_calling)

    - Handle streaming differences

    - Update session persistence

- [ ] Tâche 4.2: Update error handling & recovery

  - Owner: Senior Dev

  - Deliverable: Error handling module

  - Effort: 5h

  - Error types to handle:
enum GeminiErrorType {
AUTH_ERROR, // Invalid API key
RATE_LIMIT_EXCEEDED, // 1000 req/24h hit
INVALID_PROMPT, // Content safety block
CONTEXT_TOO_LARGE, // > 1M tokens
API_ERROR, // 5xx errors
NETWORK_ERROR, // Timeout, DNS, etc.
}

// Recovery strategies
interface ErrorRecovery {
AUTH_ERROR: () => retry(0), // Don't retry
RATE_LIMIT_EXCEEDED: () => queue(12h), // Queue for later
INVALID_PROMPT: () => handle(refine), // Ask user to refine
CONTEXT_TOO_LARGE: () => split(), // Chunk the prompt
API_ERROR: () => retry(exponential), // Exponential backoff
NETWORK_ERROR: () => retry(exponential),
}

- [ ] Tâche 4.3: Run existing test suite

  - Owner: Senior Dev

  - Deliverable: Test report (aim for 70%+ passing)

  - Effort: 4h

  - Command:
npm run test 2>&1 | tee test-report.txt

Expected output:

✓ Tests: 150 passed, 45 failed (70% pass rate)

✓ No critical compilation errors

✗ Failed tests: [list related to Claude/Gemini differences]

Jour 16-17: Integration Testing

- [ ] Tâche 4.4: Create integration tests (mocked API)

  - Owner: Senior Dev

  - Deliverable: tests/integration/gemini-integration.test.ts

  - Effort: 6h

  - Test scenarios:
describe('Integration: Agent with Gemini', () => {
// Mock Gemini responses
const mockGenAI = new MockGeminiAPI();

it('should execute single task end-to-end', async () => {
const result = await agent.executeTask('write hello world', {});
expect(result.success).toBe(true);
expect(result.output).toContain('hello');
});

it('should maintain session context across calls', async () => {
const session = new Session();
await agent.chat('my name is Bob', { session });
const response = await agent.chat('what is my name?', { session });
expect(response).toContain('Bob');
});

it('should handle rate limiting gracefully', async () => {
mockGenAI.setRateLimitAfter(10);
// Execute 15 tasks
// Expect: first 10 succeed, 11-15 queued
});
});

Semaine 5 (3-9 février 2026)

Jour 18: Real API Testing (Optional)

- [ ] Tâche 5.1: Optional E2E test against real Gemini API

  - Owner: Senior Dev

  - Deliverable: E2E test results

  - Effort: 4h (optional, may skip if time-constrained)

  - Caution: Uses Gemini free tier quota

  - Test:

Set real API key

export GEMINI_API_KEY="..."
npm run test:e2e

Expected: Single task completes successfully

Jour 19-20: Phase 1 Validation

- [ ] Tâche 5.2: Code review & cleanup

  - Owner: Lead Arch

  - Deliverable: Code review checklist signed off

  - Effort: 4h

  - Checklist:

Code Review Phase 1

    - [ ] All adapter methods implemented

    - [ ] Error handling comprehensive

    - [ ] Tests cover happy path + error cases

    - [ ] No console.log() (use logger)

    - [ ] Type safety: no any types

    - [ ] Comments on complex logic

    - [ ] Package.json dependencies pinned

    - [ ] No secrets in code (use env vars)

    - [ ] Performance baseline established

- [ ] Tâche 5.3: Documentation update

  - Owner: Senior Dev

  - Deliverable: /docs/MIGRATION_CLAUDE_TO_GEMINI.md

  - Effort: 3h

  - Content:

Migration Guide: Claude → Gemini

What Changed

API Calls

| Feature | Claude | Gemini | Adapter |
| --- | --- | --- | --- |
| Content generation | messages.create() | models.generateContent() | ✓ Abstracted |
| Token counting | countTokens() | countTokens() | ✓ Same signature |
| Streaming | stream() | streaming in config | ✓ Handled |
| Function calling | tool_use blocks | function_calling | ✓ Adapted |

Known Differences

    - Context Window: 200K (Claude) → 1M (Gemini)

    - Rate Limits: Per-model (Claude) → 1000 req/24h free tier (Gemini)

    - Error codes: Different enum values

    - Streaming format: Different chunk structure

Implementation Notes

    - Adapter pattern decouples SDK from business logic

    - All LLM calls go through LLMService

    - Tests mock the adapter, not Gemini API directly

Future Work

    - [ ] Support for other Gemini models (Gemini 2.0 Pro, etc.)

    - [ ] Multi-model support (Claude + Gemini)

    - [ ] Caching integration (Gemini Cache API)

- [ ] Tâche 5.4: Phase 1 Gate Decision

  - Owner: Lead Arch

  - Deliverable: Go/No-Go for Phase 2

  - Effort: 2h

  - Gate criteria:

Phase 1 Gate Criteria

✓ Acceptance (GO to Phase 2) if:

    - [ ] At least 1 end-to-end task works with Gemini

    - [ ] 70%+ existing tests pass

    - [ ] countTokens() validated (matches Gemini API)

    - [ ] Error handling covers 80%+ of cases

    - [ ] No blocking technical issues identified

  - ✗ Re-planning (NO-GO) if:

    - [ ] Critical Gemini API incompatibility discovered

    - [ ] Performance unacceptable (> 2x Claude)

    - [ ] Streaming broken or inconsistent

    - [ ] Token counting unreliable

  - Decision: ☐ GO ☐ NO-GO

If GO: Proceed immediately to Phase 2
If NO-GO: Pivot criteria or timeline adjustment

PHASE 2: MIGRATION UI (Semaines 6-8)

Objectif: Remplacer Electron par Oclif, créer CLI avec TUI moderne
Livrable: CLI fully fonctionnel, feature parity avec Auto-Claude
Succès: User peut exécuter workflows via CLI, TUI responsive

Semaine 6 (10-16 février 2026)

Jour 21-22: Oclif Setup & Architecture

- [ ] Tâche 6.1: Initialize Oclif framework

  - Owner: Senior Dev

  - Deliverable: Oclif scaffolding created

  - Effort: 3h

  - Steps:

Initialize oclif in existing project

npx oclif init

This creates:

├── src/commands/ (CLI commands)

├── src/index.ts (Entry point)

├── bin/run.js (Binary wrapper)

└── oclif.json (Config)

- [ ] Tâche 6.2: Design CLI command structure

  - Owner: Lead Arch

  - Deliverable: Command hierarchy document

  - Effort: 4h

  - CLI structure:

Auto-Gemini-CLI Command Structure

auto-gemini
├── init # Initialize new workspace
│ └── --name # Workspace name
├── task # Create & execute task
│ ├── new # Define new task
│ ├── run ID # Execute task
│ ├── list # List tasks
│ └── delete ID # Remove task
├── chat # Interactive chat mode
│ ├── --session # Resume session
│ └── --model # Override model
├── config # Manage configuration
│ ├── set KEY VALUE # Set config
│ ├── get KEY # Get config
│ └── show # Show all config
├── session # Manage sessions
│ ├── list # List all sessions
│ ├── show ID # Show session details
│ ├── clear ID # Clear session
│ └── export ID # Export session history
├── status # Show system status
│ └── --watch # Live status
├── logs # View execution logs
│ ├── tail # Stream logs
│ ├── grep PATTERN # Search logs
└── help # Show help

Examples:

$ auto-gemini task new "write a CLI tool"
$ auto-gemini task run <task-id>
$ auto-gemini chat
$ auto-gemini config set model gemini-2.0-pro

- [ ] Tâche 6.3: Create base command classes

  - Owner: Senior Dev

  - Deliverable: Base command architecture

  - Effort: 4h

  - File: src/base-command.ts:
import { Command, Flags } from '@oclif/core';
import { logger } from './utils/logger';
import { config } from './config/environment';

export abstract class BaseCommand extends Command {
protected logger = logger;
protected config = config;

// Common flags
static baseFlags = {
debug: Flags.boolean({
description: 'Enable debug logging',
default: false,
}),
'config-dir': Flags.string({
description: 'Override config directory',
default: config.app.dataDir,
}),
};

async init(): Promise<void> {
if (this.flags.debug) {
this.logger.setLevel('debug');
}
}
}

Jour 23-24: Core Commands Implementation

- [ ] Tâche 6.4: Implement init command

  - Owner: Senior Dev

  - Deliverable: src/commands/init.ts

  - Effort: 4h

  - Functionality:
// src/commands/init.ts
export default class Init extends BaseCommand {
async run(): Promise<void> {
// 1. Ask for workspace name
// 2. Create directory structure
// 3. Initialize SQLite database
// 4. Create default config file
// 5. Validate Gemini API key
// 6. Test API connection
this.log('✓ Workspace initialized at ./auto-gemini');
}
}

- [ ] Tâche 6.5: Implement task run command

  - Owner: Senior Dev

  - Deliverable: src/commands/task/run.ts

  - Effort: 6h

  - Functionality:
// src/commands/task/run.ts
// Key features:
// - Load task from database
// - Execute with Gemini
// - Show live progress (spinner)
// - Stream output to terminal
// - Save result to session

Semaine 6 Closure

- [ ] Tâche 6.6: Test basic CLI workflow

  - Owner: Senior Dev

  - Deliverable: CLI test results

  - Effort: 2h

  - Test:
$ npm run dev -- init --name test-workspace
$ npm run dev -- task new "hello world"
$ npm run dev -- task run <id>

Expected: Should complete without errors

Semaine 7 (17-23 février 2026)

Jour 25-26: TUI Components

- [ ] Tâche 7.1: Create TUI components (Ink.js or Blessed)

  - Owner: Senior Dev

  - Deliverable: TUI component library

  - Effort: 8h

  - Components:
// src/tui/components/
├── Spinner.tsx # Loading spinner
├── ProgressBar.tsx # Progress indication
├── StatusBar.tsx # Bottom status bar
├── TaskOutput.tsx # Streaming output display
├── ErrorDisplay.tsx # Error messages with colors
└── InteractivePrompt.tsx # User input

- [ ] Tâche 7.2: Implement chat interactive mode

  - Owner: Senior Dev

  - Deliverable: src/commands/chat.ts

  - Effort: 6h

  - Features:

    - [x] REPL interface (readline-based)

    - [x] Session persistence

    - [x] Streaming responses

    - [x] Command history

    - [x] Exit gracefully

Jour 27-28: Session Management UI

- [ ] Tâche 7.3: Implement session list and session show

  - Owner: Senior Dev

  - Deliverable: src/commands/session/*.ts

  - Effort: 5h

  - Output format:
$ auto-gemini session list

ID | Created | Tasks | Last Modified
-----------+--+
sess-001 | 2026-01-20 | 5 | 1 hour ago
sess-002 | 2026-01-15 | 12 | 2 days ago

$ auto-gemini session show sess-001

Session: sess-001
Created: 2026-01-20 14:30:00
Tasks executed: 5
Total tokens: 45,000

History:
[14:30] Task: "write hello world" → ✓
[14:32] Task: "optimize code" → ✓
...

- [ ] Tâche 7.4: Implement config commands

  - Owner: Senior Dev

  - Deliverable: src/commands/config.ts

  - Effort: 3h

Semaine 8 (24-2 mars 2026)

Jour 29-30: Feature Completeness

- [ ] Tâche 8.1: Implement remaining commands

  - Owner: Senior Dev

  - Deliverable: All commands from Phase 2 spec

  - Effort: 8h

  - Commands to complete:

    - task list, task delete

    - logs tail, logs grep

    - status --watch

    - All help pages

- [ ] Tâche 8.2: Test complete CLI flow

  - Owner: Senior Dev

  - Deliverable: Comprehensive CLI tests

  - Effort: 6h

  - Test scenarios:

Scenario 1: New user workflow

$ auto-gemini init
$ auto-gemini task new "write hello world"
$ auto-gemini task run <id>
$ auto-gemini session show <id>

Scenario 2: Chat mode

$ auto-gemini chat

Hello
What is my name?
exit

Scenario 3: Configuration

$ auto-gemini config set model gemini-2.0-pro
$ auto-gemini config get model
$ auto-gemini config show

Jour 31: Polish & Phase 2 Gate

- [ ] Tâche 8.3: Code cleanup & documentation

  - Owner: Senior Dev + Lead Arch

  - Deliverable: Clean codebase

  - Effort: 4h

  - Checklist:

    - [x] Remove console.log() (use logger)

    - [x] Add JSDoc comments

    - [x] CLI help text complete

    - [x] No broken links in docs

- [ ] Tâche 8.4: Phase 2 Gate Decision

  - Owner: Lead Arch

  - Deliverable: Go/No-Go for Phase 3

  - Effort: 2h

  - Gate criteria:

Phase 2 Gate Criteria

✓ Acceptance (GO to Phase 3) if:

    - [ ] All core commands working (init, task, chat, config)

    - [ ] CLI responsive and user-friendly

    - [ ] TUI components smooth (no lag)

    - [ ] Session persistence working

    - [ ] Help documentation complete

    - [ ] No critical bugs

  - ✗ Re-planning (NO-GO) if:

    - [ ] TUI performance poor (>500ms latency)

    - [ ] Commands broken or inconsistent

    - [ ] Session data corrupt

  - Decision: ☐ GO ☐ NO-GO

PHASE 3: OPTIMISATION GEMINI (Semaines 9-12)

Objectif: Optimiser pour Gemini specifics (rate limiting, context, caching)
Livrable: Production-ready system, performance baseline, documentation
Succès: Passe load tests, handles constraints gracefully, monitoring active

Semaine 9 (3-9 mars 2026)

Jour 32-33: Rate Limiting System

- [ ] Tâche 9.1: Implement token-bucket rate limiter

  - Owner: Senior Dev

  - Deliverable: src/services/rate-limiter.ts

  - Effort: 6h

  - Strategy:
// Rate limit: 1000 requests / 24 hours
// Strategy: Token-bucket queue with SQLite persistence

interface RateLimitConfig {
maxRequests: number; // 1000
windowSeconds: number; // 86400 (24 hours)
burstSize: number; // Allow 10 consecutive
}

class RateLimiter {
async canMakeRequest(): Promise<boolean> {
// Check if we have tokens available
// If yes: consume token, return true
// If no: queue request, return false
}

async queueRequest(task: Task): Promise<QueueID> {
// Persist to DB with scheduled execution time
// Emit event when task becomes executable
}
}

- [ ] Tâche 9.2: Implement request queue & scheduler

  - Owner: Senior Dev

  - Deliverable: Queue management system

  - Effort: 6h

  - Features:

    - [x] Persistent queue (SQLite)

    - [x] Scheduled execution (cron-like)

    - [x] Priority levels (high, normal, low)

    - [x] Retry logic (exponential backoff)

Jour 34-35: Context Window Management

- [ ] Tâche 9.3: Implement context manager for 1M tokens

  - Owner: Senior Dev

  - Deliverable: src/services/context-manager.ts

  - Effort: 8h

  - Strategy:
class ContextManager {
maxTokens: number = 1_000_000;
currentTokens: number = 0;

async validatePrompt(prompt: string): Promise<ValidationResult> {
const tokens = await this.countTokens(prompt);
if (currentTokens + tokens > maxTokens) {
return {
valid: false,
availableTokens: maxTokens - currentTokens,
suggestedChunking: calculateChunks(prompt),
};
}
return { valid: true };
}

async addToContext(content: string): Promise<void> {
const tokens = await this.countTokens(content);
this.currentTokens += tokens;
}
}

- [ ] Tâche 9.4: Implement context window cleanup

  - Owner: Senior Dev

  - Deliverable: Sliding window & compression

  - Effort: 4h

  - Strategies:

    - Sliding window (remove oldest messages)

    - Compression (summarize old context)

    - Chunking (split large tasks)

Semaine 10 (10-16 mars 2026)

Jour 36-37: Performance Optimization

- [ ] Tâche 10.1: Optimize Gemini API calls

  - Owner: Senior Dev

  - Deliverable: Performance baseline & optimizations

  - Effort: 8h

  - Optimizations:

Performance Optimizations

    - Streaming Optimization

      - Enable streaming for large outputs

      - Emit chunks as they arrive (don't buffer)

      - Reduces apparent latency

    - Caching Strategy

      - Cache countTokens() results (same prompt)

      - Cache API responses (if safe)

      - Use Gemini Cache API (if available)

    - Batch Requests (future)

      - If multiple tasks queued, batch API calls

      - Reduce API overhead

    - Model Selection

      - Small tasks: gemini-2.0-flash (faster, cheaper)

      - Complex tasks: gemini-2.0-pro (more powerful)

      - Auto-detect based on complexity

- [ ] Tâche 10.2: Implement monitoring & metrics

  - Owner: Senior Dev

  - Deliverable: Metrics collection system

  - Effort: 5h

  - Metrics to track:

Key Metrics

    - API Response Time (p50, p95, p99)

    - Tokens Used / Task

    - Queue Depth

    - Error Rate by Type

    - Session Duration

    - Success Rate

  - Tools:

    - Prometheus (optional, for advanced monitoring)

    - Simple JSON logging for now

Jour 38-39: Testing & Validation

- [ ] Tâche 10.3: Create load tests

  - Owner: Senior Dev

  - Deliverable: Load testing suite

  - Effort: 6h

  - Scenarios:
// Load test: Execute 100 tasks sequentially
// Measure: API latency, queue behavior, memory growth

async function loadTest() {
for (let i = 0; i < 100; i++) {
const task = task-${i};
const start = Date.now();
await agent.executeTask(task);
const duration = Date.now() - start;
console.log(Task ${i}: ${duration}ms);
}
}

// Expected results:
// - p50: < 500ms
// - p95: < 2000ms
// - Memory: stable (no leaks)
// - Queue: processes at rate limit

- [ ] Tâche 10.4: Create stress tests

  - Owner: Senior Dev

  - Deliverable: Stress testing suite

  - Effort: 4h

  - Scenarios:

    - 1000+ token context

    - Very long prompts

    - Rapid-fire requests

    - Network failures/timeouts

Semaine 11 (17-23 mars 2026)

Jour 40-41: Error Handling & Resilience

- [ ] Tâche 11.1: Comprehensive error handling

  - Owner: Senior Dev

  - Deliverable: Error recovery strategies for all Gemini errors

  - Effort: 6h

  - Error types handled:

    - [x] Rate limiting (RESOURCE_EXHAUSTED)

    - [x] Auth failures (PERMISSION_DENIED)

    - [x] Content safety (INVALID_ARGUMENT)

    - [x] Context window overflow

    - [x] Network timeouts

    - [x] Malformed responses

- [ ] Tâche 11.2: Implement circuit breaker

  - Owner: Senior Dev

  - Deliverable: Circuit breaker pattern implementation

  - Effort: 4h

  - States:

    - CLOSED: Normal operation

    - OPEN: API failing, reject requests

    - HALF_OPEN: Testing if API recovered

Jour 42-43: Documentation & Examples

- [ ] Tâche 11.3: Write comprehensive documentation

  - Owner: Senior Dev + Lead Arch

  - Deliverable: /docs/USER_GUIDE.md, /docs/API.md

  - Effort: 8h

  - Content:

User Guide

Installation

npm install -g auto-gemini-cli

or

npx auto-gemini-cli init

Quick Start

$ auto-gemini init
$ auto-gemini task new "write hello world"
$ auto-gemini task run <id>

Configuration

API Key

export GEMINI_API_KEY="..."
auto-gemini config set apiKey $GEMINI_API_KEY

Rate Limiting

    - Free tier: 1000 requests/24h

    - Monitor queue: auto-gemini status --watch

    - Scheduled execution: Automatic

Troubleshooting

Rate Limit Exceeded

    - Tasks queued automatically

    - Check status: auto-gemini status

    - Manually clear: auto-gemini session clear <id>

Context Window Full

    - Auto-chunking enabled

    - Or: Reduce task scope

    - Or: Start new session

- [ ] Tâche 11.4: Create example workflows

  - Owner: Senior Dev

  - Deliverable: Example scripts & documentation

  - Effort: 4h

  - Examples:

    - Code generation workflow

    - Documentation writing

    - Bug analysis workflow

Semaine 12 (24-30 mars 2026)

Jour 44-45: Integration Testing

- [ ] Tâche 12.1: Run comprehensive integration tests

  - Owner: Senior Dev

  - Deliverable: Integration test suite results

  - Effort: 8h

  - Test coverage:

Integration Tests

    - [ ] Rate limiter queues requests correctly

    - [ ] Context manager prevents overflow

    - [ ] Error recovery works for each error type

    - [ ] Streaming continues after network hiccup

    - [ ] Sessions persist across restarts

    - [ ] Parallel tasks don't corrupt state

    - [ ] Memory stable over 24h simulation

- [ ] Tâche 12.2: Performance benchmarking

  - Owner: Senior Dev

  - Deliverable: Performance report

  - Effort: 4h

  - Baseline metrics:
Task Execution Time:

    - Simple (< 100 tokens): 200-500ms

    - Medium (100-1000 tokens): 500-2000ms

    - Large (1000+ tokens): 2000-5000ms

  - Memory Usage:

    - Idle: < 50MB

    - Single session: < 100MB

    - Multi-session (10): < 200MB

  - API Overhead:

    - countTokens() call: ~50ms

    - generateContent() call: ~200-1000ms (varies)

Jour 46-47: Phase 3 Gate

- [ ] Tâche 12.3: Production readiness review

  - Owner: Lead Arch + Senior Dev

  - Deliverable: Production readiness checklist

  - Effort: 6h

  - Checklist:

Production Readiness Checklist

Code Quality

    - [ ] No console.log() statements

    - [ ] All errors have appropriate recovery

    - [ ] Logging is comprehensive

    - [ ] Type safety: no any types

    - [ ] Performance baseline established

    - [ ] Memory leaks tested & verified none

Operations

    - [ ] Health check endpoint works

    - [ ] Logging to file for analysis

    - [ ] Error tracking integrated (Sentry)

    - [ ] Metrics exported (Prometheus optional)

    - [ ] Documentation complete & accurate

Security

    - [ ] API key never logged

    - [ ] Secrets not in repository

    - [ ] SQLite database encrypted (optional)

    - [ ] Rate limiting prevents abuse

    - [ ] Input validation comprehensive

Testing

    - [ ] Unit tests: > 80% coverage

    - [ ] Integration tests: all critical paths

    - [ ] Load tests: < 2s p95 latency

    - [ ] Stress tests: handles edge cases

    - [ ] E2E tests: against real Gemini API

Deployment

    - [ ] Build process automated

    - [ ] Docker image created (optional)

    - [ ] Executable binary tested

    - [ ] Installation documented

    - [ ] Upgrade path documented

- [ ] Tâche 12.4: Phase 3 Gate Decision

  - Owner: Lead Arch

  - Deliverable: Go/No-Go for Phase 4

  - Effort: 2h

  - Gate criteria:

Phase 3 Gate Criteria

✓ Acceptance (GO to Phase 4) if:

    - [ ] Rate limiting working correctly

    - [ ] Context manager prevents overflows

    - [ ] Performance meets baseline

    - [ ] Error handling comprehensive

    - [ ] Load tests pass (p95 < 2s)

    - [ ] No known bugs

    - [ ] Production readiness > 90%

  - ✗ Re-planning (NO-GO) if:

    - [ ] Performance far below baseline

    - [ ] Rate limiting buggy

    - [ ] Memory leaks detected

  - Decision: ☐ GO ☐ NO-GO

PHASE 4: INTÉGRATION & RELEASE (Semaines 13-14)

Objectif: Tester e2e, finaliser documentation, déployer v1.0
Livrable: v1.0 release, documentation complète, support ready
Succès: v1.0 dans npm registry, utilisable en production

Semaine 13 (31 mars - 6 avril 2026)

Jour 48-49: Final Testing

- [ ] Tâche 13.1: Execute comprehensive E2E tests

  - Owner: Senior Dev

  - Deliverable: E2E test results (real Gemini API)

  - Effort: 8h

  - Test scenarios:

Scenario 1: Fresh install

npm install -g auto-gemini-cli
auto-gemini init
auto-gemini config set apiKey $GEMINI_API_KEY
auto-gemini task new "write a fibonacci function"
auto-gemini task run <id>

Expected: Task completes successfully

Result stored in session

Scenario 2: Long-running task

auto-gemini task new "analyze this large repository" # 500K+ tokens
auto-gemini task run <id> --watch

Expected: Auto-chunks, shows progress, completes

Scenario 3: Rate limiting

for i in {1..20}; do
auto-gemini task new "task i"auto-geminitaskruntask-i --no-wait
done
auto-gemini status --watch

Expected: First 10 run, rest queued

Queue processes as rate limit allows

Scenario 4: Error recovery

(Manually trigger network failure)

Expected: Circuit breaker engages, retries work

- [ ] Tâche 13.2: User acceptance testing (if stakeholders available)

  - Owner: Desjardins stakeholders + Lead Arch

  - Deliverable: Feedback & sign-off

  - Effort: 4h

  - Feedback areas:

    - CLI UX (is it intuitive?)

    - Performance (is it fast enough?)

    - Documentation (is it clear?)

    - Reliability (does it work consistently?)

Jour 50-51: Documentation & Examples

- [ ] Tâche 13.3: Finalize documentation

  - Owner: Senior Dev + Lead Arch

  - Deliverable: Complete documentation suite

  - Effort: 8h

  - Documents to create/update:

    - README.md (overview, quick start)

    - INSTALLATION.md (detailed install)

    - USER_GUIDE.md (step-by-step)

    - API.md (command reference)

    - TROUBLESHOOTING.md (common issues)

    - ARCHITECTURE.md (technical details)

    - MIGRATION.md (from Auto-Claude)

    - CONTRIBUTING.md (for future contributors)

- [ ] Tâche 13.4: Create changelog & release notes

  - Owner: Lead Arch

  - Deliverable: CHANGELOG.md, release notes

  - Effort: 2h

  - Content:

CHANGELOG

v1.0.0 - 2026-05-01

Major Features

    - ✨ Gemini CLI: Full adaptation of Auto-Claude for Gemini API

    - ✨ Rate limiting: Automatic queue management (1000 req/24h)

    - ✨ Context management: Handle up to 1M token contexts

    - ✨ Interactive chat: REPL mode with session persistence

    - ✨ Performance: Streaming responses, fast token counting

Breaking Changes

    - Electron UI removed (CLI only)

    - Config file format slightly different

    - API key env var: GEMINI_API_KEY (was CLAUDE_API_KEY)

Migration

    - See MIGRATION.md for moving from Auto-Claude

Known Limitations

    - Free tier: 1000 requests/24h (Google limit)

    - No multi-model support yet

    - No caching API integration yet

Contributors

    - André-Guy Bruneau (Lead Architect)

    - [Team members]

Semaine 14 (7-13 avril 2026)

Jour 52-53: Build & Publishing

- [ ] Tâche 14.1: Create build artifacts

  - Owner: Lead Arch

  - Deliverable: Packaged binaries & npm package

  - Effort: 4h

  - Artifacts:

Build executable

npm run build

Package for different platforms (optional)

npm run package:macos
npm run package:linux
npm run package:windows

Output:

dist/

├── auto-gemini-cli-1.0.0.tar.gz

├── auto-gemini-cli-1.0.0.exe

└── auto-gemini-cli-1.0.0.dmg

- [ ] Tâche 14.2: Publish to npm registry

  - Owner: Lead Arch

  - Deliverable: npm package published

  - Effort: 2h

  - Steps:

Verify package.json

npm version major # This is v1.0.0

Test publish (optional)

npm publish --dry-run

Publish to npm

npm publish

Verify

npm search auto-gemini-cli
npm view auto-gemini-cli@1.0.0

- [ ] Tâche 14.3: Create GitHub release

  - Owner: Lead Arch

  - Deliverable: GitHub release page

  - Effort: 1h

  - Content:

    - Release notes (copy from CHANGELOG)

    - Binaries attached

    - Installation instructions

    - Known issues

Jour 54-55: Release & Support

- [ ] Tâche 14.4: Announce release

  - Owner: Lead Arch

  - Deliverable: Release announcement

  - Effort: 2h

  - Channels:

    - GitHub releases

    - Email to stakeholders

    - Internal documentation

    - (Optional: blog post, Twitter, etc.)

- [ ] Tâche 14.5: Setup support & issue tracking

  - Owner: Lead Arch

  - Deliverable: Support guidelines, issue templates

  - Effort: 2h

  - Checklist:

Support Setup

    - [ ] GitHub issues enabled

    - [ ] Issue templates created (.github/ISSUE_TEMPLATE/)

    - [ ] Discussions enabled

    - [ ] Slack channel #auto-gemini-cli-support

    - [ ] Email support alias set up

    - [ ] Response time SLAs defined

  - Issue Templates:

    - Bug Report

    - Feature Request

    - Question

    - Documentation Issue

Jour 56: Final Validation & Gate

- [ ] Tâche 14.6: v1.0 Sign-off

  - Owner: Lead Arch + Desjardins Leadership

  - Deliverable: Official sign-off

  - Effort: 2h

  - Final checklist:

v1.0 Release Sign-Off

Technical

    - [ ] All tests passing (unit, integration, E2E)

    - [ ] Performance baseline met

    - [ ] No critical bugs

    - [ ] Documentation complete

    - [ ] Code reviewed & approved

Operational

    - [ ] npm package published

    - [ ] GitHub release created

    - [ ] Support process ready

    - [ ] Monitoring active

Stakeholder

    - [ ] Desjardins approval received

    - [ ] Budget tracking complete

    - [ ] Timeline met (or documented variance)

    - [ ] Deliverables accepted

  - Sign-off: ☐ APPROVED FOR PRODUCTION

Date: _______________
By: André-Guy Bruneau (Lead Architect)
For: Desjardins

- [ ] Tâche 14.7: Post-Release Planning

  - Owner: Lead Arch

  - Deliverable: Roadmap for future versions

  - Effort: 2h

  - Future work:

Post-v1.0 Roadmap

v1.1 (2-3 months after v1.0)

    - [ ] Gemini Cache API integration

    - [ ] Multi-model support (Claude + Gemini)

    - [ ] Web UI (optional)

    - [ ] Plugin system

v2.0 (6+ months after v1.0)

    - [ ] Distributed execution (multi-machine)

    - [ ] Advanced scheduling

    - [ ] Workflow orchestration

    - [ ] Team collaboration features

Community

    - [ ] Contribute guidelines

    - [ ] Plugin template

    - [ ] Community examples repo

DÉPENDANCES & BLOCKERS

Dépendances Critiques

Phase 0:
└─→ Approval budgétaire Desjardins (CRITICAL)
└─→ Phase 1 begins

Phase 1:
└─→ Gemini API stable & available (CRITICAL)
└─→ Codebase analysis complete
└─→ Phase 2 begins

Phase 2:
└─→ Phase 1 complete (at least MVP working)
└─→ Oclif framework understood
└─→ Phase 3 begins

Phase 3:
└─→ Phase 2 complete (CLI working)
└─→ Load testing tools available
└─→ Phase 4 begins

Phase 4:
└─→ Phase 3 complete (optimization done)
└─→ npm account available
└─→ Release to npm

Potential Blockers & Mitigation

| Blocker | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Gemini API breaking change | 2-3 weeks delay | MEDIUM | Monitor API status, use adapters |
| Codebase more coupled than expected | 1-2 weeks delay | MEDIUM | Design refactoring upfront |
| Team member unavailable | Timeline slip | LOW | Cross-train both team members |
| Performance unacceptable | 1 week delay | LOW | Optimize streaming, caching |
| Rate limiting impossible to work around | Pivot needed | LOW | Fall back to Scenario 3 (Claude) |
| Gemini free tier discontinued | Costs increase | LOW | Switch to paid tier or Scenario 3 |

Risk Mitigation Actions

- Weekly risk review: Every Monday, assess blockers

- Slack #auto-gemini-risks: Real-time communication

- Decision framework: If blocker > 2 days impact, escalate immediately

- Buffer time: 2-3 weeks reserved for unexpected delays

MÉTRIQUES DE SUCCÈS

Phase-by-Phase Success Metrics

| Phase | Key Metrics | Target | Measurement |
| --- | --- | --- | --- |
| 0 | Approval % | 100% | Budget signed |
|  | Codebase understood | Yes | ADRs written |
|  | Team ready | Yes | Env setup complete |
| 1 | API swap working | Yes | E2E test passes |
|  | Tests passing | 70%+ | Test report |
|  | Token counter validated | Yes | countTokens tests |
| 2 | Commands functional | 100% | CLI tests pass |
|  | TUI responsive | <500ms | Latency test |
|  | User can complete workflow | Yes | User test successful |
| 3 | Rate limiting works | Yes | Queue test passes |
|  | Context management works | Yes | 1M token test |
|  | Performance baseline met | Yes | Benchmarks pass |
| 4 | v1.0 released to npm | Yes | npm publish successful |
|  | Documentation complete | Yes | All docs reviewed |
|  | Zero critical bugs | Yes | Bug report review |

Overall Project Success Metrics

Timeline: 14 weeks (3.5 months) ✓ vs original 19 weeks
Cost: $13-34K ✓ vs original $100-150K
Features: 100% of Phase 1-4 scope ✓
Quality: >80% test coverage ✓
Performance: p95 < 2s ✓
Uptime (day 1 of release): >95% ✓
User satisfaction: >4/5 ✓
Zero production hotfixes needed ✓

GESTION DES RISQUES

Risk Register

Risk #1: Gemini API Incompatibility

- Description: Critical incompatibility between Claude and Gemini APIs discovered during Phase 1

- Probability: MEDIUM (50%)

- Impact: HIGH (2-3 weeks delay)

- Mitigation: Adapter pattern designed to isolate API differences

- Owner: Senior Dev

- Action: Daily API testing, early detection

Risk #2: Performance Unacceptable

- Description: Gemini API slower than Claude, impacting user experience

- Probability: LOW (20%)

- Impact: MEDIUM (1 week delay)

- Mitigation: Implement streaming, caching, optimize before Phase 4

- Owner: Senior Dev

- Action: Performance profiling in Phase 3

Risk #3: Rate Limiting Not Workable

- Description: 1000 req/24h limit too restrictive for use cases

- Probability: LOW (15%)

- Impact: HIGH (complete pivot)

- Mitigation: Pivot to Scenario 3 (Claude Code) as backup

- Owner: Lead Arch

- Action: Have Scenario 3 plan ready

Risk #4: Team Member Unavailable

- Description: One team member becomes unavailable mid-project

- Probability: LOW (10%)

- Impact: MEDIUM (1-2 weeks delay)

- Mitigation: Cross-train both team members early

- Owner: Lead Arch

- Action: Shared knowledge sessions Week 1-2

Risk #5: Scope Creep

- Description: Additional features requested mid-project

- Probability: MEDIUM (60%)

- Impact: MEDIUM (timeline slip)

- Mitigation: Strict change control, defer to v1.1

- Owner: Lead Arch

- Action: Weekly stakeholder alignment

Risk Monitoring

- Weekly risk review: Every Monday in standup

- Escalation path: If risk impacts > 2 days, escalate to Lead Arch

- Risk board: GitHub project "Risks" tab

- Contingency time: 2-3 weeks buffer built into timeline

BUDGET DÉTAILLÉ

Cost Breakdown

PHASE 0: Préparation (2 weeks)
├── Lead Architect (1 FTE): 1.0 × 2 × $200/hr = $1,600
├── Senior Dev (0.5 FTE): 0.5 × 2 × $200/hr = $800
└── Subtotal: = $2,400

PHASE 1: Swap API (3 weeks)
├── Lead Architect (1 FTE): 1.0 × 3 × $200/hr = $2,400
├── Senior Dev (0.5 FTE): 0.5 × 3 × $200/hr = $1,200
├── Testing tools (optional): = $500
└── Subtotal: = $4,100

PHASE 2: UI Migration (3 weeks)
├── Lead Architect (0.5 FTE): 0.5 × 3 × $200/hr = $1,200
├── Senior Dev (1 FTE): 1.0 × 3 × $200/hr = $2,400
├── Design review: = $300
└── Subtotal: = $3,900

PHASE 3: Optimization (4 weeks)
├── Lead Architect (0.5 FTE): 0.5 × 4 × $200/hr = $1,600
├── Senior Dev (1 FTE): 1.0 × 4 × $200/hr = $3,200
├── Load testing tools: = $500
├── Monitoring (Sentry free): = $0
└── Subtotal: = $5,300

PHASE 4: Release (2 weeks)
├── Lead Architect (1 FTE): 1.0 × 2 × $200/hr = $1,600
├── Senior Dev (0.5 FTE): 0.5 × 2 × $200/hr = $800
├── Documentation review: = $300
└── Subtotal: = $2,700

INFRASTRUCTURE & TOOLS:
├── GitHub (free): = $0
├── npm (free): = $0
├── Google Gemini (free tier): = $0
├── Sentry (free): = $0
├── Slack (existing): = $0
└── Subtotal: = $0

─────────────────────────────────────────────────────

TOTAL PROJECT COST: $18,400

Contingency (10% for unknowns): $ 1,840
─────────────────────────────────────────────────────

TOTAL BUDGET (with contingency): $20,240

APPROVED BUDGET RANGE: $13-34K
STATUS: ✓ WITHIN RANGE

Budget Allocation by Cost Center

Labor Costs (FTE Hours):
├── Lead Architect: 1.0 × 14 weeks × 40h/week × $200/hr = $11,200
├── Senior Dev: 0.5 × 14 weeks × 40h/week × $200/hr = $5,600
└── Total Labor: = $16,800

Tools & Services: = $1,300
├── Testing tools: $500
├── Monitoring: $300 (Sentry optional)
├── Design review: $300
├── Documentation: $200

Contingency (10%): = $1,840

TOTAL: = $20,240

Cost Savings Opportunities

- Reuse Auto-Claude code: Saves ~30% development (vs Scenario 1)

- Leverage Gemini free tier: No API costs (1000 req/24h)

- Use free tools: GitHub, npm, Sentry free tier

- Cross-training: Avoids hiring additional staff

Cost Tracking

Weekly cost tracking:

- Team hours logged (time tracking)

- Tool subscriptions tracked

- Contingency reserve managed

- Budget variance reported

Monthly stakeholder report:

- Actual vs planned spending

- Forecast to completion

- Risk adjustments

CHECKLIST FINALE

Pre-Launch (Semaine 13)

- [ ] All phases completed

- [ ] All tests passing (>90%)

- [ ] Documentation reviewed

- [ ] Performance baseline met

- [ ] Security audit passed

- [ ] Stakeholder sign-off obtained

Launch (Semaine 14)

- [ ] npm package published

- [ ] GitHub release created

- [ ] Announcement sent

- [ ] Support team ready

- [ ] Monitoring active

- [ ] Rollback plan documented

Post-Launch (First 2 weeks)

- [ ] Monitor error rates (target: <1%)

- [ ] Track user feedback

- [ ] Respond to support requests (<4h)

- [ ] Document lessons learned

- [ ] Plan v1.1 features

CONCLUSION

Planification complète pour Scénario 2: Adaptation Auto-Claude vers Auto-Gemini-CLI

- Durée totale: 14 semaines (3.5 mois), livraison ~1er mai 2026

- Effort: 1.5 FTE (Lead Architect + Senior Developer)

- Budget: $13-34K (plus ou moins contingency)

- Approche: Itérative par phases, avec gates de décision claire

- Succès défini: v1.0 production-ready, documenté, testé, releasé

Prochaines étapes:

- Obtenir approbation budgétaire formelle de Desjardins

- Assembler équipe (Lead Arch + Senior Dev)

- Commencer Phase 0 semaine de 6 janvier 2026

- Hold bi-weekly stakeholder reviews

Contact & Questions: André-Guy Bruneau (agbruneau)